## Project Data
Project ID | Program | Initiative | Task | Owner | Start Date | Due Date | Status | Priority | Risk Level | Compliance Category | Compliance Status | % Complete | Day Remaining | Overdue Flag
P001 | EOP | Participant Engagement | Advisor Meeting Tracking | Isaiah | 2026-03-02 | 2026-05-15 | In Progress | High | Medium | Engagement Requirement | Non-Compliant | 70% | 50 | On Track
P001 | EOP | Participant Engagement | Attendance | Mariah | 2026-03-02 | 2026-03-16 | Completed | Low | Low | Attendance Tracking | Compliant | 100% | -10 | Completed
P001 | EOP | Participant Engagement | Participant Follow Up Logs | Jordan | 2026-04-01 | 2026-05-01 | To Do | Medium | High | Communication Logs | Non-Compliant | 0% | 36 | On Track
P002 | ETS | Recruitment | High School Visit Tracking | Mariah | 2026-01-03 | 2026-05-15 | In Progress | High | Low | Outreach Documentation | Non-Compliant | 75% | 50 | On Track
P002 | ETS | Recruitment | Application Tracking | Ralpael | 2026-01-03 | 2026-05-15 | In Progress | High | Medium | Application Reporting | Non-Compliant | 65% | 50 | On Track
P002 | ETS | Recruitment | Follow up-Communication | Alex | 2026-04-30 | 2026-05-15 | To Do | Medium | High | Communication logs | Non-Compliant | 0% | 50 | On Track
P003 | UB | Summer Bridge | Enrollement Verification | Isaiah | 2026-03-16 | 2026-04-15 | In Progress | High | Medium | Enrollement Compliance | Non-Compliant | 25% | 20 | On Track
P003 | UB | Summer Bridge | Orientation Schedueling | Mario | 2026-04-01 | 2026-04-30 | To Do | High | Medium | Program Schedueling | Non-Compliant | 10% | 35 | On Track
P003 | UB | Summer Bridge | Faculty Cooridnation | Nathan | 2026-03-01 | 2026-03-16 | Completed | High | Low | Instructor Coordination | Compliant | 100% | -10 | Completed
P004 | UBMS | Reporting | KPI Dashboard Update | Isaiah | 2026-04-01 | 2026-04-24 | In Progress | High | Medium | Reporting Accuracy | Non-Compliant | 35% | 29 | On Track
P004 | UBMS | Reporting | Data Validatiion | Ashlie | 2026-04-26 | 2026-05-01 | To do | High | Medium | Data Integrity | Non-Compliant | 0% | 36 | On Track
P004 | UBMS | Reporting | Stakeholder Report | Steve | 2026-04-27 | 2026-05-01 | In Progress | High | Medium | Executive Reporting | Non-Compliant | 50% | 36 | On Track
Formulas:
Day Remaining = [Due Date]-TODAY()
Overdue Flag = IF(TRIM([Status])="Completed","Completed",IF(INT([Due Date])<TODAY(),"Overdue","On Track"))

## Analysis
Row Labels | Count of Task | Row Labels | Count of Task |  | Row Labels | Count of Task
Completed | 2 | Compliant | 2 |  | High | 2
In Progress | 6 | Non-Compliant | 10 |  | Low | 3
To Do | 4 | Grand Total | 12 |  | Medium | 7
Grand Total | 12 |  |  |  | Grand Total | 12
Row Labels | Count of Task | Row Labels | Sum of % Complete |  | Row Labels | Count of Task
Alex | 1 | Completed | 200% |  | EOP | 3
Ashlie | 1 | On Track | 330% |  | ETS | 3
Isaiah | 3 | Grand Total | 5.3 |  | UB | 3
Jordan | 1 |  |  |  | UBMS | 3
Mariah | 2 |  |  |  | Grand Total | 12
Mario | 1
Nathan | 1
Ralpael | 1 | Count of Task | Column Labels
Steve | 1 | Row Labels | Compliant | Non-Compliant | Grand Total
Grand Total | 12 | EOP | 1 | 2 | 3
|  | ETS |  | 3 | 3
|  | UB | 1 | 2 | 3
|  | UBMS |  | 3 | 3
|  | Grand Total | 2 | 10 | 12

## Dashboard
Key Performance Indicators
Total Tasks | % Completed | Overdue Tasks | % Compliant
12 | 44.17% | 0 | 15.38%